## Sheet1
TIMELINE
Week 1 |  | STATUS | 7th June-12 June
1 | Finalize requirements & SRS | DONE
2 | Set up Git repository
3 | Initialize React.js project with Bootstrap/CSS | In Progress
4 | Set up Django project & connect to MySQL
5 | Design database schema & create tables | DONE
Week 2 |  |  | 13 June-18 June
1 | Build authentication UI (login, signup forms)
2 | Implement Django user models, authentication
3 | Set up role distinction (student/admin)
4 | Connect frontend forms to backend APIs
5 | Test user registration & login end-to-end
Week 3 |  |  | 19 June-24 June
1 | Create event listing UI (student dashboard)
2 | Build Django event models & APIs
3 | Display events on frontend
4 | Implement event registration (students)
5 | Prevent duplicate registrations in backend
6 | Students can view their registered events
Week 4 |  |  | 25 June -1 July
1 | Build admin login/dashboard UI
2 | Implement admin APIs for event-wise participant lists
3 | Display participant data in admin dashboard
4 | Add role-based access control (frontend & backend)
5 | Basic client-side form validation
Week 5 |  |  | 2 July-8 July
1 | End-to-end testing of all flows
2 | UI/UX improvements (responsive design)
3 | Security checks (password encryption, session)
4 | Prepare user/admin demo accounts
5 | Write documentation (README, user manual)
6 | Prepare for final submission/demo